## problems
Risk Management Plan - problems occured |  |  | next ID: | #N/A
Risk ID | Overall Priority | Topic | Risk Description | Probability of Occurrence | Consequence | Impact | Risk Mitigation Strategy | Mitigation Action assigned to | Risk identified by person | Risk Identified on date | Status | Last change | What was changed | Planned Closing Date | Actual closing date | Reason to Close | Timeframe | Done Risk Mitigation Action(s)
| 3 | Project | Legality of audio playback | 1 | Not able to use Spotify API | 3 | Changing platform | Patryk | Patryk | 2021-10-14 | closed | https://community.spotify.com/t5/Archived-Chat/Can-I-use-my-account-when-at-a-party/td-p/437130 | Answer from Community Mentor / Troubleshooter clears up private (noncommercial) usage | N/A | 2021-10-14 | Solved | N/A | N/A
| 3 | Product | OneDrive cloud dies and docummentation is gone | 1 | Documents are gone | 3 | Regular documentation backups | Patryk | Patryk | 2021-10-14 | closed | Backups performed | Backups performed | N/A | 2021-10-14 | Solved | N/A | Backups performed
| 4 | Technology | Native Java Android offers terrible UI options | 2 | Using UI Java libraries | 2 | Integrating different libraries early | Design Team | Patryk | 2021-10-14 | open | N/A | N/A | ASAP | N/A | N/A | N/A | N/A
| 3 | Process | Developer not able to attend in-person meeting | 3 | Meeting in person not possible | 1 | Meeting held online | Everyone | Patryk | 2021-10-14 | open | N/A | N/A | N/A | N/A | N/A | N/A | 14.10.2021 meeting changed to online
| 9 | Skill | Lack of knowledge in a technology | 3 | Extra time spent on learning | 3 | Team member exchanging tasks | Everyone | Patryk | 2021-10-14 | open | N/A | N/A | ASAP | N/A | N/A | N/A | N/A
| 3 | Process | Developer not able to attend meeting | 3 | Meeting has to be moved | 1 | Changing meeting time | Everyone | Patryk | 2021-10-14 | open | N/A | N/A | ASAP | N/A | N/A | N/A | 07.10.2021 meeting moved to 5:30PM on thursdays
| 3 | Customer | New platform required | 1 | New platform port has to be developed | 3 | (None, customer does not exist) | Everyone | Patryk | 2021-10-14 | closed | N/A | N/A | N/A | 2021-10-14 | No customer exists | N/A | N/A
| 1 | Product | Github repository is deleted | 1 | Chaos in the team | 1 | Keeping repository management privileges on a responsible person | Patryk | Patryk | 2021-10-14 | closed | N/A | N/A | N/A | 2021-10-14 | No open management permission on repository | N/A | Invited everyone as collaborators
| 9 | Process | Development takes much longer time than anticipated ( or planned ) | 3 | Product gets delayed | 3 | Regular checks on the team progress, and providing collaboration when needed to speed up the process |  | Duygu | 2021-10-20 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3 | Process | A group member or members having to leave the project ( temporary sick leave or permanently leaving ) | 1 | Product gets delayed or other group members have to be assigned for the vacant position | 3 | ( None, risk can occur in time and might not be foreseen easily ) |  | Duygu | 2021-10-20 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2 | Process | Realization of a missing feature at a later stage of development | 1 | If the missing feature is not critical ( curable ) at this point, then product gets delayed, or it is presented before completion. However if critical, then product cannot be presented and failure is unavoidable. | 2 | Making a check list of requirements, and as the project develops , updating this list when needed. |  | Duygu | 2021-10-20 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3 | Product | During the usage of the product, the access to Spotify is suddenly interrupted or broken and cannot be retrieved. ( this can likely happen due to the internet access problems ) | 1 | Not able to use Spotify API | 3 | Changing platform |  | Duygu | 2021-10-20 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2 | Process | Developer not being able to work on the product | 3 | Developer not being able to contribute his part for some time | 3 | Responsibility taken over by someone else | Everyone | Patryk | 18.11.2021 | occured
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on A3: unique ID
Note on B3: see #data
Note on E3: 1 = low 3 = high
Note on G3: 1 = low 3 = high
Note on L3: see #data#
Note on R3: Timeframe where the risk could occur, e.g.: - date to date - 'until project end' - 'project setup' - 'testing period' - ..."

## open risks
Risk Management Plan - open risks |  |  | next ID: | #N/A
Risk ID | Overall Priority | Topic | Risk Description | Probability of Occurrence | Consequence | Impact | Risk Mitigation Strategy | Mitigation Action assigned to | Risk identified by person | Risk Identified on date | Status | Last change | What was changed | Planned Closing Date | Actual closing date | Reason to Close | Timeframe | Done Risk Mitigation Action(s)
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0
Note on A3: unique ID
Note on B3: see #data
Note on E3: 1 = low 3 = high
Note on G3: 1 = low 3 = high
Note on L3: see #data#
Note on R3: Timeframe where the risk could occur, e.g.: - date to date - 'until project end' - 'project setup' - 'testing period' - ..."

## closed risks
Risk Management Plan - open risks |  |  | next ID: | #N/A
Risk ID | Overall Priority | Topic | Risk Description | Probability of Occurrence | Consequence | Impact | Risk Mitigation Strategy | Mitigation Action assigned to | Risk identified by person | Risk Identified on date | Status | Last change | What was changed | Planned Closing Date | Actual closing date | Reason to Close | Timeframe | Done Risk Mitigation Action(s)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on A3: unique ID
Note on B3: see #data
Note on E3: 1 = low 3 = high
Note on G3: 1 = low 3 = high
Note on L3: see #data#
Note on R3: Timeframe where the risk could occur, e.g.: - date to date - 'until project end' - 'project setup' - 'testing period' - ..."

## How to use
How to use:
- Fill your risk with mitigation in the folder 'open risk'
- If a risk can be closed move it to the folder 'closed risks'
- If a problem occures out of a risk, than copy it to 'problems'
- Use '#data#' as data-storage to fill the combo-boxes Topic, Impact, Occurance and person with data
- the 'Overall Priority' is a calculation with 'Probability of Occurrence' (E) and 'Impact' (G) [E*G]
-> you can add numbers for this columns (#data#) if you need to have more detail

## _data_
Meaning of Probability and Impact numbers | Probability of Occurrence | Impact | Topic | Persons | Status
low -> | 1 | 1 | Customer | Patryk | open
middle -> | 2 | 2 | Project | Amai | mitigated for
high -> | 3 | 3 | Process | Duygu | closed
|  |  | Technology | Ruslans | occured
|  |  | Product | Asyl
|  |  | Skill | Enes
Chandan
Valentin
Mobile App Team
Design Team
Backend Team
Database Team
Everyone
Note on B1: 1 = low 3 = high
Note on C1: 1 = low 3 = high

## Revision
Risk list
Revision History
Rev. no. | State | Date | Comments | Author
1 | in work | xx.xx.xxxx | Initial version | xxx