## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a party master, I want to see the queue the users made so that I can modify it if I don’t like it. | 1 | 5 |  | open
2 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 1 | 20 |  | open
3 | As a party member, I want to suggest a song so that it might get played. | 1 | 15 |  | open
4 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 1 | 20 |  | open
5 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 1 | 20 |  | open
6 | As a party member, I want a QR-Code to be able to instantly download and configure my application. | 2 | 25 |  | open
7 | As an application user, I want to use the application on my desktop and my android phone. | 3 | 30 |  | open
8 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | 2 | 10 |  | open
9 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open
10 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open
11 | As an application user, I want to have multiple language options. | 1 | 5 |  | open
12 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open
13 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open
14 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 |  | open
15 | As a party member, I want to see current played song at real time with time stamp. | 1 | 5 |  | open

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required