## Sprint 2
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
16 | As a party master, I want to have player control in the app itself | Jukify launches spotify player |  |  |  | done, party master selects entry playlist when he creates a party
3 | As a party member, I want a QR-Code to be able to instantly download and configure my application. | Party attendee can join the party using QR code |  |  |  | done
Sprint Backlog (Tasks)
ID | Description | Priority | Effort (hours) |  | Status | Persons
|  |  | estimated | required
1 | As a party member, I want to see current played song at real time with time stamp. | 3 | 5 |  | open | work started in increment 2
2 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 2 | 20 |  | open | work started in increment 2
3 | As a party member, I want a QR-Code to be able to instantly download and configure my application. | 2 | 25 | 10 | closed | done
4 | As an application user, I want to use the application on my desktop and my android phone. | 1 | 30 |  | open
5 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | 3 | 10 |  | open | work started in increment 2
6 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open
7 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open
8 | As an application user, I want to have multiple language options. | 2 | 5 |  | open | work started in increment 2
9 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open
10 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open
11 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 |  | open | work started in increment 2
12 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 2 | 20 |  | open
13 | As a party master, I want to see the queue the users made so that I can modify it if I don’t like it. | 3 | 5 |  | open | work started in increment 2
14 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 2 | 20 |  | open
15 | As a party member, I want to suggest a song so that it might get played. | 3 | 15 |  | open | work started in increment 2
16 | As a party master, I want to have player control in the app itself | 3 | 10 | 5 | closed | done, party master selects entry playlist when he creates a party

## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a party member, I want to see current played song at real time with time stamp. | 3 | 5 |  | open | work started in increment 2
2 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 2 | 20 |  | open | work started in increment 2
3 | As a party member, I want a QR-Code to be able to instantly download and configure my application. | 2 | 25 | 10 | closed | done
4 | As an application user, I want to use the application on my desktop and my android phone. | 1 | 30 |  | open
5 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | 3 | 10 |  | open | work started in increment 2
6 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open
7 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open
8 | As an application user, I want to have multiple language options. | 2 | 5 |  | open | work started in increment 2
9 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open
10 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open
11 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 |  | open | work started in increment 2
12 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 2 | 20 |  | open
13 | As a party master, I want to see the queue the users made so that I can modify it if I don’t like it. | 3 | 5 |  | open | work started in increment 2
14 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 2 | 20 |  | open
15 | As a party member, I want to suggest a song so that it might get played. | 3 | 15 |  | open | work started in increment 2
16 | As a party master, I want to have player control in the app itself | 3 | 10 | 5 | closed | done, party master selects entry playlist when he creates a party
17
18