## Tabelle1
Time Log | Software Projekt 2020/2021
|  |  |  | Name: | Valentin Dimitrov
|  |  |  | Student ID / Matrikelnummer: | 3135012
Project Week | Calendar Week | From | To | Hours | Activities
1 | 40 | 2020-09-28 | 2020-10-04 | 1:30 | Deciding the which project to take and discussing briefly what the project should be like.
2 | 41 | 2020-10-05 | 2020-10-11 | 3:00 | Team meeting, presenting overall idea to prof Baer about what the project is about, finishing vision document with the team.
3 | 42 | 2020-10-12 | 2020-10-18 | 4:00 | Discussing user stories, requirements and use cases
4 | 43 | 2020-10-19 | 2020-10-25 | 6:00 | Choosing role, Technology research, UI team meeting, Report
5 | 44 | 2020-10-26 | 2020-11-01 | 9:00 | REST research, Reading Volley library documentation, Working on Prototype, Team meatning
6 | 45 | 2020-11-02 | 2020-11-08 | 7:00 | Researching user data persistence within application, Implementing Shared Preferences
7 | 46 | 2020-11-09 | 2020-11-15 | 6:00 | Implementing create party connectivity
8 | 47 | 2020-11-16 | 2020-11-22 | 20:00 | Researching token renewal - implementation and debugging.
9 | 48 | 2020-11-23 | 2020-11-29 | 10:00 | Testing Spotify API and fetching resources on client side
10 | 49 | 2020-11-30 | 2020-12-06 | 5:00 | Reverting comits, separating test code from already implemented and working code base, implemetning search song feature
11 | 50 | 2020-12-07 | 2020-12-13 | 1:00 | Staying up to date with project
12 | 51 | 2020-12-14 | 2020-12-20
13 | 52 | 2020-12-21 | 2020-12-27
14 | 53 | 2020-12-28 | 2021-01-03
15 | 1 | 2021-01-04 | 2021-01-10
16 | 2 | 2021-01-11 | 2021-01-17
Formulas:
Calendar Week = ISOWEEKNUM([From])
To = [From]+6
From = [From, row above]+7