## Sprint 2
Sprint 3
Starts | 09.12.2021
Ends | 07.01.2022
Overall Goal | Implementing the rest of the functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | User can request party history |  |  |  | open
2 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | User can see parties he attended and their history (related to #2) |  |  |  | open
5 | As a party member, I want to be able to rate the song being played. | User can rate the song (cool/bad) |  |  |  | open
7 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | User can start a vote to skip to next song |  |  |  | open
12
15
13
Sprint Backlog (Tasks)
ID | Description | Priority | Effort (hours) |  | Status | Persons
|  |  | estimated | required
1 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 2 | 20 |  | open
2 | As an application user, I want to use the application on my desktop and my android phone. | 1 | 30 |  | open
4 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | 3 | 10 |  | open
5 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open
6 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open
7 | As an application user, I want to have multiple language options. | 2 | 5 |  | open
8 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open
9 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open
10 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 |  | open
11 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 2 | 20 |  | open
12 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 2 | 20 |  | open
13
14
15

## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 2 | 20 |  | open | almost done
2 | As an application user, I want to use the application on my desktop and my android phone. | 1 | 30 |  | open
3 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | 3 | 10 |  | open | almost done
4 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open
5 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open
6 | As an application user, I want to have multiple language options. | 2 | 5 |  | open | work started in increment 2
7 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open
8 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open
9 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 |  | open | work started in increment 2
10 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 2 | 20 |  | open
11 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 2 | 20 |  | open
12
13
14
15
16
17
18