## Tabelle1
Time Log | Software Projekt 2020/2021
|  |  |  | Name: | Chandan Jeet
|  |  |  | Student ID / Matrikelnummer: | 3134684
Project Week | Calendar Week | From | To | Hours | Activities
1 | 40 | 2020-09-28 | 2020-10-04 | 1,5h | Decided the project to be selected and its features
2 | 41 | 2020-10-05 | 2020-10-11 | 3,0h | Team meeting(Presented to Prof. Baer the project idea and its features going through the Vision doc)
3 | 42 | 2020-10-12 | 2020-10-18 | 0,5h | Regular meeting with team for roles, user stories and the requirements
4 | 43 | 2020-10-19 | 2020-10-25 | 6,0h | Discussion for selecting the technologies and checking the project risks and its presentation to Prof. Baer
5 | 44 | 2020-10-26 | 2020-11-01 | 13,0h | Meeting with the team, backend prototype study, frontend/backend connectivity (with few team members), study of python methods with spotify API development
6 | 45 | 2020-11-02 | 2020-11-08 | 5,0h | Meeting with the team, spotify API Call techniques researched & checked the compatibility with our project, github repository checks
7 | 46 | 2020-11-09 | 2020-11-15 | 9,0h | Meeting with the team, study of new graphical design for frontend improvement (Material design) started its integration, regular checks of backend connectivity with DB & frontend
8 | 47 | 2020-11-16 | 2020-11-22 | 9,0h | Meetings, manual functionality checks frontend+ backend, github repo checks, frontend Qr functionality implemented
9 | 48 | 2020-11-23 | 2020-11-29 | 10,0h | Regular team meeting, finished Qr implementation, Backend POST request implemented, Frontend Qr Scanner implementation finished + Adapter and Json Object/Array data retriever implementation started
10 | 49 | 2020-11-30 | 2020-12-06 | 16,0h | Meeting with the team + individual mettings for features implementation discussion, Frontend custom list adapter & Json functionality finished, Backend requests optimization
11 | 50 | 2020-12-07 | 2020-12-13 | 10,0h | UI updated and frontend functionality for saving "tempQueue" implemented (adapter + activity)
12 | 51 | 2020-12-14 | 2020-12-20 | 8,0h | Backend "tempQueue" implementation with Enes (worked on Linked List) + Frontend functionality for adding the song at the second position in the queue implemented
13 | 52 | 2020-12-21 | 2020-12-27 | 5,0h | Meetings + optimization of the UI
14 | 53 | 2020-12-28 | 2021-01-03 | 2,0h | Qr generation implementation for party name + UI fixes
15 | 1 | 2021-01-04 | 2021-01-10
16 | 2 | 2021-01-11 | 2021-01-17
Formulas:
Calendar Week = ISOWEEKNUM([From])
To = [From]+6
From = [From, row above]+7