## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 2 | 20 | 10 | closed | done
2 | As an application user, I want to use the application on my desktop and my android phone. | 1 | 30 |  | open | Not in first release
3 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | 3 | 10 | 10 | closed | related to #1
4 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open | Not in first release
5 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open | Not in first release
6 | As an application user, I want to have multiple language options. | 2 | 5 |  | open | Not in first release
7 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open | Not in first release
8 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open | Not in first release
9 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 | 10 | open | related to #1
10 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 2 | 20 |  | open | Not in first release
11 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 2 | 20 |  | open | Not in first release
12 | As a party member, I want to prioritise some song so it gets played earlier | 3 | 10 | 10 | closed
13
14
15
16
17
18

## Sprint 4
Sprint 4
Starts | 07.01.2022
Ends | 20.01.2022
Overall Goal | Minimum functionality implementation, full testing, release preparatio
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status | Comments
1 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | Party history |  |  |  | closed | Done
2 | As a user, I want to be able to see my own history ( what songs were suggested by me and played in the party ) . | Party history |  |  |  | closed | Done
5 | As a party member, I want to be able to rate the song being played. | User can rate a song |  |  |  | open | Not happening in first release
7 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | User can start a vote to skip to next song |  |  |  | open | Not happening in first release
12 | As a party member, I want to prioritise some song so it gets played earlier | User can prioritise a song to play earlier |  |  |  | closed | Done
15
13
Sprint Backlog (Tasks)
ID | Description | Priority | Effort (hours) |  | Status | Persons | Comments
|  |  | estimated | required
1 | As an user, I want to be able to see what songs were played at the party so that I can listen to them again. | 2 | 20 | 10 | closed | Patryk, Enes, Chandan, Ruslans | -
2 | As an application user, I want to use the application on my desktop and my android phone. | 1 | 30 | - | open |  | Not in first release
4 | As a user, I want to be able to see my own history | 3 | 10 | 10 | closed | Patryk, Enes, Chandan, Ruslans | Related to #1
5 | As a party organizer, I want to be to free and allocate new party master at will. | 2 | 15 |  | open |  | Not in first release
6 | As a party member, I want to be able to rate the song being played. | 2 | 5 |  | open |  | Not in first release
7 | As an application user, I want to have multiple language options. | 2 | 5 |  | open |  | Not in first release
8 | As a party master I want to be able to revoke and grant party members voting permissions at any point. | 2 | 10 |  | open |  | Not in first release
9 | As a party master I want to be able to kick party members out of the party. | 2 | 10 |  | open |  | Not in first release
10 | As a party master, I want to be able to share the playlist that was played at the party (after the party has happened). | 2 | 5 | 10 | closed |  | Related to #1
11 | As a party member, I want to start a skip-poll so that we can vote to skip to the next song. | 2 | 20 |  | open |  | Not in first release
12 | As a party master, I want to start a poll so that I can see if party attendees like current playlist/mood. | 2 | 20 |  | open |  | Not in first release
13 | As a party member, I want to prioritise some song so it gets played earlier | 3 | 10 | 10 | closed | Chandan, Enes | Done
14
15